## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Project Plan
| Table 1 | Project Plan
Project Plan
| Table 1 | Project Plan
Week 2
| Table 1 | Week 2
Week 1
| Table 1 | Week 1

## Project Plan
Yokohama : Emtrack Mobile App Revamp & Rebranding Development Project Plan* |  |  | Duration | Planned |  | Actual |  | Work
Sr. No. | Phases | Major Activities | Time / Days | Start Date | End Date | Start Date | End Date | Status %
1 | Project Kick-off | Introduction of Teams | 1 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 100
2 | Requirements | Overview of Requirements - Feature Mapping Old and New Screens | 3 | 2025-12-08 | 2025-12-11 | 2025-12-08 | 2025-12-11 | 100
3 |  | Requirement Analysis - API changes analysis | 4 | 2025-12-11 | 2025-12-12 | 2025-12-11 | 2025-12-12 | 100
4 |  | SRS-Requirement Document Review | 2 | 2025-12-12 | 2025-12-15 | 2025-12-12 |  | 50
5 |  | SRS-Requirement Document Sign-off | 1 | 2025-12-15 | 2025-12-15 |  |  | 0
6 | Design | Screen Design and UI | 4 | 2025-12-11 | 2025-12-15 | 2025-12-11 |  | 30
7 |  | Modern UI Design - Wireframes | 3 | 2025-12-12 | 2025-12-15 | 2025-12-12 |  | 30
8 |  | Wireframes - UI Design Review | 2 | 2025-12-16 | 2025-12-18 |  |  | 0
9 |  | Wireframes - UI Design Sign-off | 1 | 2025-12-18 | 2025-12-19 |  |  | 0
10 | Development | Login | 1 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 100
11 |  | Home | 2 | 2025-12-23 | 2025-12-24 |  |  | 0
12 |  | account-list-modal | 1 | 2025-12-26 | 2025-12-26 |  |  | 0
13 |  | add-tire | 3 | 2025-12-27 | 2025-12-30 |  |  | 0
14 |  | admin-inspection-request | 1 | 2025-12-31 | 2025-12-31 |  |  | 0
15 |  | change-location-account | 1 | 2026-01-02 | 2026-01-02 |  |  | 0
16 |  | create-new-tire | 2 | 2026-01-03 | 2026-01-05 |  |  | 0
17 |  | create-new-vehicle | 2 | 2026-01-06 | 2026-01-07 |  |  | 0
18 |  | edit-tire | 2 | 2026-01-08 | 2026-01-09 |  |  | 0
19 |  | edit-vehicle | 2 | 2026-01-10 | 2026-01-12 |  |  | 0
20 |  | filter-popup-vehicle | 1 | 2026-01-13 | 2026-01-13 |  |  | 0
21 |  | filterpopup | 2 | 2026-01-15 | 2026-01-16 |  |  | 0
22 |  | inspect-tire | 2 | 2026-01-17 | 2026-01-19 |  |  | 0
23 |  | inspect-vehicle | 2 | 2026-01-20 | 2026-01-21 |  |  | 0
24 |  | inspection-request | 2 | 2026-01-22 | 2026-01-23 |  |  | 0
25 |  | inspection-summary | 1 | 2026-01-24 | 2026-01-24 |  |  | 0
26 |  | normal-inspection-request | 1 | 2026-01-27 | 2026-01-27 |  |  | 0
27 |  | offline-sync | 1 | 2026-01-28 | 2026-01-28 |  |  | 0
28 |  | preferences | 1 | 2026-01-29 | 2026-01-29 |  |  | 0
29 |  | reject-request | 1 | 2026-01-30 | 2026-01-30 |  |  | 0
30 |  | remove-tire | 2 | 2026-01-31 | 2026-02-02 |  |  | 0
31 |  | rotate-tire | 2 | 2026-02-02 | 2026-02-03 |  |  | 0
32 |  | search-install-tire | 3 | 2026-02-04 | 2026-02-06 |  |  | 0
33 |  | search-vehicle-tyre | 2 | 2026-02-07 | 2026-02-09 |  |  | 0
34 |  | select-account-location | 2 | 2026-02-10 | 2026-02-11 |  |  | 0
35 |  | select-location | 1 | 2026-02-12 | 2026-02-12 |  |  | 0
36 |  | update-hours | 2 | 2026-02-13 | 2026-02-14 |  |  | 0
37 |  | vehicle-inspection | 2 | 2026-02-16 | 2026-02-17 |  |  | 0
38 |  | view-all-tire | 2 | 2026-02-18 | 2026-02-19 |  |  | 0
39 |  | view-all-vehicle | 2 | 2026-02-20 | 2026-02-21 |  |  | 0
40 |  | view-inspect-tire | 2 | 2026-02-23 | 2026-02-24 |  |  | 0
41 |  | view-inspections | 1 | 2026-02-25 | 2026-02-25 |  |  | 0
42 |  | view-tire | 2 | 2026-02-26 | 2026-02-27 |  |  | 0
43 |  | view-vehicle | 2 | 2026-02-28 | 2026-03-02 |  |  | 0
44 |  | view-vehicle-inspection | 2 | 2026-03-05 | 2026-03-06 |  |  | 0
45 |  | Logout | 1 | 2026-03-07 | 2026-03-07
46 |  | user management/super admin page | 5 | 2026-03-09 | 2026-03-13 |  |  | 0
47 | Unit Testing | Functional Validation (Test Cases) | 3 | 2026-03-14 | 2026-03-17 |  |  | 0
48 |  | Bug Reporting & Defect Fixing | 4 | 2026-03-18 | 2026-03-21 |  |  | 0
49 |  | Final Working Portal & share Test Cases with Yokohama | 3 | 2026-03-23 | 2026-04-25 |  |  | 0
50 | Deployment | Deployment Document creation(include User Manual) | 6 | 2026-03-26 | 2026-04-01 |  |  | 0
51 |  | Deployment | 5 | 2026-04-02 | 2026-04-07 |  |  | 0
52 |  | Ready for UAT | 5 | 2026-04-08 | 2026-04-13 |  |  | 0
53 | UAT | UAT by Business Users | 4 | 2026-04-14 | 2026-04-17 |  |  | 0
54 |  | UAT Sign-Off | 5 | 2026-04-18 | 2026-04-23 |  |  | 0
55 | VAPT Testing | VAPT Testing | 6 | 2026-04-24 | 2026-05-01 |  |  | 0
56 |  | Bug Reporting & Defect Fixing | 4 | 2026-05-02 | 2026-04-06 |  |  | 0
57 |  | Final Working Portal | 4 | 2026-05-07 | 2026-05-11 |  |  | 0
58 | Go Live | KT to Support Team | 8 | 2026-05-12 | 2026-05-21 |  |  | 0
59 |  | Deployment to Production | 15 | 2026-05-22 | 2026-06-06 |  |  | 0
60 |  | GO LIVE Sign-Off | 10 | 2026-06-08 | 2026-06-18 |  |  | 0
61 | Support/Train the Trainer | Resolve issues, if any | 10 | 2026-06-19 | 2026-06-30 |  |  | 0
Formulas:
End Date = [Planned]
End Date = [End Date]
Actual = [Planned]
Planned = [End Date, row above]
Planned = [Planned, row above]+1

## Week 2
|  | Project Kick-Start Date | 2024-12-08
|  | Week # | 2
|  | Project Phase | Screen Design, Review and Sign-Off
|  | WK - Start Date | 2025-12-15
|  | WK - End Date | 2025-12-19
Sr. | Date | Major Activities | Sub-Task | Status | SPOC | Resolution | Close Date | Remarks
1 | 2025-12-15 | Design | Screen Design and UI | Completed
2 | 2025-12-16 | Design | Modern UI Design - Wireframes | Completed
3 | 2025-12-17 | Design | Wireframes - UI Design | Completed
4 | 2025-12-18 | Design | Wireframes - UI Design | Completed
5 | 2025-12-19 | Design | Wireframes - UI Design Document sent for Review & Signoff | Completed
Formulas:
Date = [Date, row above]+1

## Week 1
|  | Project Kick-Start Date | 2024-12-08
|  | Week # | 1
|  | Project Phase | Scope Review and Sign-Off
|  | WK - Start Date | 2025-12-08
|  | WK - End Date | 2025-12-12
Sr. | Date | Major Activities | Sub-Task | Status | SPOC | Resolution | Close Date | Remarks
1 | 2025-12-08 | Requirements | Project Kick-off meeting | Completed
2 | 2025-12-09 | Requirements | Overview of Requirements & Requirement Analysis | Completed
3 | 2025-12-10 | Requirements | SRS Document Creation | Completed
4 | 2025-12-11 | Requirements | SRS Document Creation | Completed
5 | 2025-12-12 | Requirements | SRS Document walkthru and sent for Review & Signoff | Completed
Formulas:
Date = [Date, row above]+1